## Sheet1
AUTOSAR Project Plan Team 5
Update 1 Dated : 10/05/2017
The plan started from May 5,2017, and the project shall be delivered on May 27,2017 |  |  |  | EA Sub-Team | Ahmed Tourkey (L)
Mina Makram
|  |  |  | EEP Sub-Team | Sherif Darwish
Abd El-Rahman Abbas
S/N | Process | No. Of Days | From | To | Sub-Team | Status
1 | Read SWS of EA & EEP | 2 | 2017-05-05 | 2017-06-05 | ALL | Done 6/5/2017
2 | Write and read from E2PROM of TivaC | 3 | 2017-07-05 | 2017-09-05 | EEP | Done 8/5/2017
3 | Create Dependancies File/s for EA Module | 2 | 2017-07-05 | 2017-08-05 | EA | Done 7/5/2017
4 | Create Interface File/s For EA Module | 2 | 2017-09-05 | 2017-10-05 | EA | Done 8/5/2017
5 | Create Dependancies File/s for EEP Driver | 2 | 2017-10-05 | 2017-11-05 | EEP | Done 10/5/2017
6 | Create Config File/s For EA Module | 2 | 2017-11-05 | 2017-12-05 | EA | In progress
7 | Create Interface File/s For EEP Driver | 2 | 2017-12-05 | 13/5/2017 | EEP | Done 10/5/2017
8 | Start Implementation in EA Module ( Static C and H files ) | 5 | 13/5/2017 | 17/5/2017 | EA | Waiting
9 | Create Config File/s For EEP Driver | 2 | 14/5/2017 | 15/5/2017 | EEP | In progress
10 | Start Implementation in EEP Driver ( Static C and H files ) | 5 | 16/5/2017 | 20/5/2017 | EEP | Waiting
11 | Testing EA Module | 2 | 18/5/2017 | 19/5/2017 | EA | Waiting
12 | Create Test cases for EA and EEP to start integration process | 2 | 20/5/2017 | 21/5/2017 | EA | Waiting
13 | Testing EEP Driver on TivaC | 2 | 21/5/2017 | 22/5/2017 | EEP | Waiting
14 | Integration of EA module and EEP Driver with the created test cases | 5 | 23/5/2017 | 27/5/2017 | ALL | Waiting